## BoQ - Site 1
SITE 1: Filling of the excavated area that have been excavated for the new flood gate foundation at site 1, near the existing 4 barrel flood gate (15x15x4m size)
|  |  |  | 1 | 3
Item No. | Description | Unit | Qty | Rate | Total Amount FJD (VIP) | Work Duration
1 | Red clay |  |  |  |  | Two Weeks (Including Saturdays)
| Supply and delivery of red clay to site 1, near the existing 4 barrel flood gate | m³ | 600 |  | 0
| Fill and compact approved backfill red clay in the excavated area at site 1 (refer to Appendix 1a - Schematic photo part 1 for reference) | m³ | 600 |  | 0
2 | Opening of the two outlets of the existing flood gate barrels toward river side, which have been closed by the current contractor. This removal includes the removal of red clay and bulker bags placed at the face of the two outlets ( Refer Appendix 1a - Schematic photo Part 2). Also remove the existing sticks holding/closing the two of the 4 barrel doors of the existing flood gate (refer to Appendix 1a - Schematic photo Part 3 for reference) | Lump Sum | 1 |  | 0
Total of Cost |  |  |  |  | 0

## Material List - Site 1
SITE 1: Filling of the excavated area that have been excavated for the new flood gate foundation at site 1 (Near the existing 4 barrel flood gate)
Item No. | Description | Unit | Qty | Work Duration
1 | Red clay |  |  | Two Weeks (Including Saturdays)
| Supply and delivery of red clay to site 1, near the existing 4 barrel flood gate | m³ | 600
| Fill and compact approved backfill red clay in the excavated area at site 1 (refer to Appendix 1a - Schematic photo part 1 for reference) | m³ | 600
2 | Opening of the two outlets of the existing flood gate barrels toward river side, which have been closed by the current contractor. This removal includes the removal of red clay and bulker bags placed at the face of the two outlets ( Refer to Appendix 1a - Schematic photo Part 2). Also remove the existing sticks holding/closing the two of the 4 barrel doors of the existing flood gate (refer to Appendix 1a - Schematic photo Part 3 for reference) | Lump Sum | 1